## Sheet1
Release Type | Release 1A
Qa Status | (Multiple Items)
Count of Dev Status | Column Labels
Row Labels | In Progress | Not Possible | Open | Resolved | Grand Total
Kishore |  | 1 | 2 | 4 | 7
Praneeth | 1 |  |  |  | 1
RK |  |  | 2 |  | 2
Sajitha |  |  | 1 |  | 1
Shekar |  |  |  | 2 | 2
Shekar/Kishore |  |  |  | 1 | 1
Shekar/Praneeth |  |  | 1 | 1 | 2
Sumukesh |  |  |  | 9 | 9
Sumukesh/RK |  |  | 1 |  | 1
Sumukesh/Shekar |  |  | 1 |  | 1
Grand Total | 1 | 1 | 8 | 17 | 27

## Internal Issues
S.No | Issue ID | Module | Pages Name | Issue Description | Date Identified | Reported By | Severity | Priority | Type | Dev Fixed Date | Dev Status | Assigned To | Q/A Status | Developer Comments | Live Status | Testing Status | Testing Comments | Updated Date | Test Scenario ID | Test Case ID | Finding
1 | BG_001 | User Management |  | After creating a user, the verification email is sent, but clicking the "Verify Email" button gives a 403 error. The toast message says "Verified and set password," but the email is not actually verified. - major bug | 2025-08-10 | Internal | Critical | High | Functional | 2025-08-11 | Resolved |  | Resolved | [8 empty] | TRUE
2 | BG_002 | User Management |  | App logo and first-time-change-password page issues (missing or incorrect display). | 2025-08-10 | Internal | Medium | High | UI | 2025-08-11 | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
3 | BG_003 | User Management |  | Manufacturing rep can see the Super Admin. If a rep deactivates Super Admin or Admin, those accounts cannot log in to the site. | 2025-08-10 | Internal | Medium | High | Functional | 2025-08-11 | Resolved | RK | Resolved | [8 empty] | TRUE
4 | BG_004 | User Management |  | When creating a new role (e.g., "Mini User"), the role does not appear in the dropdown when creating a user. | 2025-08-10 | Internal | Medium | High | Fuctional | 2025-08-11 | Resolved | RK | Resolved | [8 empty] | TRUE
5 | BG_005 | User Management |  | If any status is changed to active/inactive, in roles.the user is immediately logged out from the site. | 2025-08-10 | Internal | Medium | High | Functional | 2025-08-11 | Resolved | RK | Resolved | [8 empty] | TRUE
6 | BG_006 | User Management |  | In super admin page Not all user are getting from data base. In the tabel | 2025-08-11 | Internal | Medium | High | Functional | 2025-08-11 | Resolved | RK | Resolved | [8 empty] | TRUE
7 | BG_007 | User Management |  | while roles are assigned to some on if we delete that role it was deleting but want the message not to delete the role. | 2025-08-12 | Internal | Medium | High | Functional | 2025-08-21 | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
8 | BG_008 | User Management |  | User can also seeing the creating roles page and if inactivate the admin. Adimin can not login. | 2025-08-12 | Internal | Medium | High | Functional | 2025-08-11 | Resolved | RK | Resolved | [8 empty] | TRUE
9 | BG_009 | User Management |  | User friendly errors. | 2025-08-12 | Internal | Medium | Low | Functional |  | Resolved |  | Resolved | [8 empty] | TRUE
10 | BG_010 | User Management |  | Search is working for in active roles page. But active search is not working . | 2025-08-12 | Internal | Medium | Medium | Functional |  | Resolved |  | Resolved | [8 empty] | TRUE
11 | BG_011 | User Management |  | password encrprtion. | 2025-08-12 | Internal | Medium | High | Functional | 2025-08-21 | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
12 | BG_012 | User Management |  | Role Permissions page make create as (view, edit,delete) | 2025-08-12 | Internal | Medium | High | Functional |  | Resolved |  | Resolved | [8 empty] | TRUE
13 | BG_013 | User Management |  | When super Admin is (Inactive) mini User role. super Admin is loging out. But what to oppsite role is loging out. | 2025-08-12 | Internal | Medium | High | Functional |  | Resolved |  | Resolved | [8 empty] | TRUE
14 | BG_014 | User Management |  | Ridhima Bhandekar88 is (admin) hase the removing the acess of super admin permission role. | 2025-08-12 | Internal | Medium | High | Functional |  | Resolved |  | Resolved | [8 empty] | TRUE
15 | BG_015 | User Management |  | Edit screen is not working. Showing an 403 issue. in super AdminPage | 2025-08-12 | Internal | Medium | High | Functional |  | Resolved |  | Resolved | [8 empty] | TRUE
16 | BG_016 | User Management |  | if super admin want to create manufacturning and. It togels Apar Sales Executive Drop down, in that drop down. Insted of APar Sales Executive Get mini users. | 2025-08-12 | Internal | Medium | High | Functional |  | Resolved |  | Resolved | [8 empty] | TRUE
17 | BG_017 | User Management |  | INactive User getting Mails.For Forget password Mails. | 2025-08-12 | Internal | Medium | High | Functional |  | Resolved |  | Resolved | [8 empty] | TRUE
18 | BG_018 | User Management |  | removing permission to the dashboard for admin still vewing the dashboard. | 2025-08-13 | Internal | Medium | Low | Functional | 2025-08-21 | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
19 | BG_019 | User Management |  | if make the role inactive still viewing role in the role permission page. Super admin. | 2025-08-13 | Internal | Medium | Low | Functional |  | Resolved |  | Resolved | [8 empty] | TRUE
20 | BG_020 | User Management |  | eye button is missing in the login page. | 2025-08-13 | Internal | Medium | Low | Functional |  | Resolved |  | Resolved | [8 empty] | TRUE
21 | BG_021 | User Management |  | after making email verfiction still making manuall activetion | 2025-08-13 | Internal | Medium | Low | Functional |  | Resolved |  | Resolved | [8 empty] | TRUE
22 | BG_022 | User Management |  | Once I enter text in the global search bar, if I clear all filters in the table, it also clears the data from the global search bar. | 2025-08-18 | Internal | Medium | Low | Functional |  | Resolved |  | Resolved | [8 empty] | TRUE
23 | BG_023 | User Management |  | Duplicate entry is being allowed for role names. | 2025-08-18 | Internal | Medium | High | Functional | 2025-08-21 | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
24 | BG_024 | User Management |  | The toaster message (UI) is unreadable in some scenarios as it overlaps with the screen content. | 2025-08-18 | Internal | Medium | Low | UI |  | Resolved |  | Resolved | [8 empty] | TRUE
25 | BG_025 | User Management |  | After clicking Verify mail, I am still able to access the verfication email again. | 2025-08-18 | Internal | Medium | High | Functional |  | Resolved |  | Resolved | [8 empty] | TRUE
26 | BG_026 | User Management |  | There is no difference between the error message and the success message. | 2025-08-18 | Internal | Medium | Low | UI |  | Resolved |  | Resolved | [8 empty] | TRUE
27 | BG_027 | User Management |  | The bug is that it does not give permission to view, but it gives permission to edit and delete. However, when I log in and check, it does not actually give edit or delete permission. Make the edit and delete options automatically check the view permission checkbox when selected. | 2025-08-18 | Client | Medium | Low | Functional |  | Resolved |  | Resolved | [8 empty] | TRUE
28 | BG_028 | User Management |  | global search bar not working. | 2025-08-18 | Internal | Medium | Low | Medium |  | Not an Issue | Shekar | Resolved | [8 empty] | FALSE
29 | BG_029 | User Management |  | Adimin giving permission to delete the use but the to manfacturning rep. if manafturning rep is try to delete or edit it is gettin error. | 2025-08-19 | Internal | Medium | Low | Medium |  | Resolved |  | Resolved | [8 empty] | TRUE
30 | BG_030 | User Management |  | The system displays a generic "Authentication failed" message for incorrect username or password; it should specify whether the issue is an invalid login ID, incorrect password, or non-existent user. | 2025-08-19 | Client | Medium | Low | UI | 2025-08-21 | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
31 | BG_031 | User Management |  | Global search on the User List page functions only for First Name, Last Name, and Email, but does not support Mobile Number, Role, or Status. | 2025-08-19 | Client | Medium | Low | Ui | 2025-08-21 | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
32 | BG_032 | User Management |  | Sorting by User ID is not working; clicking the sort button does not arrange the IDs in ascending or descending order. | 2025-08-19 | Client | Medium | Low | UI |  | Resolved |  | Resolved | [8 empty] | TRUE
33 | BG_033 | User Management |  | The "Active" filter in the local search is non-functional and does not return results. | 2025-08-19 | Client | Medium | Low | UI | 2025-08-21 | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
34 | BG_034 | User Management |  | The password field displays two overlapping "view password" icons, which should be corrected to show only one. | 2025-08-19 | Client | Medium | Low | UI |  | Resolved | Shekar | Resolved | [8 empty] | TRUE
35 | BG_035 | User Management |  | The "Self Deactivate Account" feature should be disabled for Admins and lower roles, and enabled only for Super Admins. | 2025-08-19 | Client | Medium | Low | Functional | 2025-08-21 | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
36 | BG_036 | User Management |  | Super Admins currently do not have access to edit user names or email addresses. | 2025-08-19 | Client | Medium | Low | Functional | 2025-08-21 | Not an Issue | Sumukesh | Resolved | Not an Issue | [7 empty] | FALSE
37 | BG_037 | User Management |  | Duplicate name was entering in the role like ex:- "SuperAdmin adding like SuperAdMiN). It is taking. | 2025-08-19 | Internal | Medium | Low | Functional | 2025-08-21 | Not an Issue | Sumukesh | Resolved | Not an Issue | [7 empty] | FALSE
38 | BG_038 | User Management |  | User add,edit, delete toster messages are same as previous. in the Supe Admin Page. | 2025-08-20 | Internal | Medium | Low | UI |  | Resolved |  | Resolved | [8 empty] | TRUE
39 | BG_039 | User Management |  | i am created the new user now it is not showing the grid in the user tabel | 2025-08-20 | Internal | Medium | Low | Functional |  | Resolved |  | Resolved | [8 empty] | TRUE
40 | BG_040 | User Management |  | once the role was deactive. it is deactive role was missing in the grid. | 2025-08-20 | Internal | Medium | Low | Functional |  | Resolved |  | Resolved | [8 empty] | TRUE
41 | BG_041 | User Management |  | Admins are currently able to deactivate Super Admins, which should be restricted. | 2025-08-19 | Client | Medium | Low | Functional | 2025-08-21 | Resolved | Sumukesh | Resolved | No provision to see the same level user/role | [7 empty] | TRUE
42 | BG_042 | User Management |  | When an Admin deactivates another Admin (or a Super Admin deactivates another Super Admin), the system should handle self-deactivation appropriately. | 2025-08-19 | Client | Medium | Low | Functional | 2025-08-21 | Resolved | Sumukesh | Resolved | No provision to see the same level user/role | [7 empty] | TRUE
43 | BG_043 | User Management |  | Admin and Super Admin roles currently have the ability to delete their own accounts, which should be restricted. | 2025-08-19 | Client | Medium | Low | Functional | 2025-08-21 | Resolved | Sumukesh | Resolved | No provision to see the same level user/role | [7 empty] | TRUE
44 | BG_044 | User Management |  | After successfully creating one user, subsequent attempts result in a "Failed to create user" error. | 2025-08-19 | Client | Medium | Low | Functional |  | Resolved |  | Resolved | [8 empty] | TRUE
45 | BG_045 | User Management | Add user | While creating a Mini User, the option to tag a Manufacturing Representative is missing. | 2025-08-19 | Client | Medium | Low | Functional |  | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
46 | BG_046 | User Management |  | The APAR logo is not displayed as the favicon (website icon) on the browser tab. | 2025-08-19 | Client | Medium | Low | Functional |  | Resolved |  | Resolved | [8 empty] | TRUE
47 | BG_047 | User Management |  | The system response is delayed; sometimes, when logged in as Super Admin, the User List shows "No user found" despite users being present. | 2025-08-19 | Client | Medium | Low | Functional |  | Resolved | Shekar | Resolved | [8 empty] | TRUE
48 | BG_048 | User Management |  | Selecting "Edit" permission without "View" results in the module being invisible to the user; "Edit" should automatically include "View" access. | 2025-08-19 | Client | Medium | Low | Functional |  | Resolved |  | Resolved | [8 empty] | TRUE
49 | BG_049 | User Management |  | The "View User Profile" feature is not working for any user. | 2025-08-19 | Client | Medium | Low | Functional |  | Resolved |  | Resolved | View profile Yet to do this functionality | [7 empty] | TRUE
50 | BG_050 | User Management |  | The "User Type" filter in the User List view should support multi-select functionality. | 2025-08-19 | Client | Medium | Low | Functional |  | Resolved |  | Resolved | [8 empty] | TRUE
51 | BG_051 | Master | Lme | The portal currently displays LME pricing only for Aluminium; Copper LME values should also be included. | 2025-08-19 | Client | Medium | Low | Functional |  | Resolved | Shekar | Resolved | Masters Yet to do this functionality | [7 empty] | TRUE
52 | BG_052 | User Management |  | The system allows creation of users with invalid email addresses (e.g., "jish@invalid.com"); proper email validation should be implemented. | 2025-08-19 | Client | Medium | Low | Functional | 2025-08-21 | Not an Issue | Sumukesh | Resolved | Not an Issue | [7 empty] | FALSE
53 | BG_053 | User Management | Edit User | Admins do not have access to manually tag APAR Sales Executives to Manufacturing Representatives in the "Edit User" section. | 2025-08-19 | Client | Medium | Low | Functional |  | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
54 | BG_054 | User Management |  | When registering a user with an already registered email ID, the system throws a generic "HTTP Error"; it should display a clear message such as "Email ID already registered." | 2025-08-19 | Client | Critical | Low | Functional |  | Resolved |  | Resolved | [8 empty] | TRUE
55 | BG_055 | User Management |  | UI is transparent and overlapping with other pages | 2025-08-20 | Client | Critical | Low | Functional | 2025-08-21 | Resolved | Kishore | Resolved | [8 empty] | TRUE
56 | BG_056 | User Management |  | When the admin logs in to the role permissions page, they turn off the super Admin permissions restricted permission. | 2025-08-20 | Internal | Critical | Low | Functional | 2025-08-21 | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
57 | BG_057 | User Management |  | When "Forgot Password" is clicked, a temporary password is generated. If we use this temporary password, it logs in directly to the dashboard without additional verification. | 2025-08-21 | Internal | Critical | High | Functional | 2025-08-22 | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
58 | BG_058 | User Management | Edit User | In the Admin section, the edit field is not displaying the dropdown list for selecting an "Apar Sales Executive." | 2025-08-21 | Internal | Medium | High | Functional |  | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
59 | BG_059 | User Management | User List | The Admin is able to view the mini users, but this access needs to be restricted. | 2025-08-21 | Internal | Medium | High | Functional |  | Resolved | Sumukesh | Resolved | Not an Issue | [7 empty] | TRUE
60 | BG_060 | User Management |  | If the Admin user is given permission to edit roles, they are able to remove the Super Admin permissions, which should not be allowed. | 2025-08-21 | Internal | Medium | Medium | Functional | 2025-08-21 | Resolved | Sumukesh | Resolved | No provision to see the same level user/role | [7 empty] | TRUE
61 | BG_061 | User Management |  | For example, consider a role named 'Apar Sales Executive' that is linked to the 'Manufacturing Rep' role. What if we attempt to delete the 'Apar Sales Executive' role? Should the system allow deletion, or should it prevent it to protect existing user assignments? | 2025-08-21 | Internal | Medium | Medium | Functional | 2025-08-21 | Resolved | Sumukesh | Resolved | No deletion if the user exist |  |  | Not getting the front end Page it is deleting |  |  |  |  | TRUE
62 | BG_062 | User Management | Edit User | In the Super Admin application, on the Edit User page, when selecting the role dropdown as Manufacturing Rep, the APAR Sales Rep linkage is not appearing. | 2025-08-22 | Internal | Medium | Medium | Functional |  | Resolved | Sumukesh | Resolved | No role edditing possible | [7 empty] | TRUE
63 | BG_063 | Product Master | Product | Product Master while adding the new product getting the error it is giving the 403. | 2025-08-23 | Internal | Medium | Medium | Functional |  | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
64 | BG_064 | Master | Conduter | Master moduel adding Conduter type Edit, Add is not working. | 2025-08-23 | Internal | Medium | Medium | Functional |  | Resolved | Subbu | Resolved | [8 empty] | TRUE
65 | BG_065 | Master | Insulation | Insulation master was total differnet UI. No drop down all other things mising. | 2025-08-23 | Internal | Medium | Medium | Functional |  | Resolved | Subbu | Resolved | [8 empty] | TRUE
66 | BG_066 | User Management | Add user | There is star In the tabel grid. Which is located at the mobile number field.(*)- | 2025-08-25 | Internal | Medium | Medium | UI | Resolved | Resolved | Subbu | Resolved | [8 empty] | TRUE
67 | BG_067 | User Management | Role Permission | All check box are looking the orange. But in the role permission page filter checkbox is looking in the blue. | 2025-08-25 | Internal | Medium | Medium | UI | Resolved | Resolved | Subbu | Resolved | [8 empty] | TRUE
68 | BG_068 | All Pages | All pages | No of records per page UI is different across all pages compare - Users and Masters | 2025-08-25 | Internal | Medium | Medium | UI |  | Resolved | Shekar | Resolved | Masters and User module i have adjusted | [7 empty] | TRUE
69 | BG_069 |  | All pages | Filters in the header are different compare with Master and user module | 2025-08-25 | Internal | Medium | Medium | UI | Resolved | Resolved | Subbu | Resolved | [8 empty] | TRUE
70 | BG_070 | Master | Products | Products page showing a toster message like all products are loaded successfully - on loading of the page | 2025-08-25 | Internal | Medium | Medium | UI | Resolved | Resolved | Subbu | Resolved | [8 empty] | TRUE
71 | BG_071 | Master | Customer VA % | Edit Customer VA Percentage Edit popup: In the edit popup there are two dropdonw values like Product Cat name and Conductor type bothe dropdowns are displaying in different view | 2025-08-25 | Internal | Medium | Medium | UI |  | Resolved | Kishore | Resolved | [8 empty] | TRUE
72 | BG_072 | Master | Insulation | Insulation Master page is in different view | 2025-08-25 | Internal | Medium | Medium | UI |  | Resolved |  | Resolved | [8 empty] | TRUE
73 | BG_073 | Customer | Customer Category | Customer Categories Getting No Data. | 2025-08-25 | Internal | Medium | Medium | Functional | Resolved | Resolved | Kishore | Resolved | [8 empty] | TRUE
74 | BG_074 | Master | Manufacturing Rep Commissions | Manufacturing Rep Commissions is getting no data | 2025-08-25 | Internal | Medium | Medium | UI |  | Resolved | RK | Resolved | [8 empty] | TRUE
75 | BG_075 | Master | LME | LME price getting error. | 2025-08-25 | Internal | Medium | Medium | Resolved |  | Resolved | RK | Resolved | [8 empty] | TRUE
76 | BG_076 | Customer | Customer | Custmoer Page. Getting the old Grid. Like with search box. | 2025-08-25 | Internal | Medium | Medium | UI |  | Resolved | Shekar | Resolved | [8 empty] | TRUE
77 | BG_077 | User Management | edit User | Mobile no is empty field is displaying when we are edit the field and update the information | 2025-08-25 | Internal | Medium | Medium | Functional | Resolved | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
78 | BG_078 | User Management | Edit User | The APAR Sales Executive dropdown is not working. | 2025-08-25 | Internal | Medium | Medium | Functional |  | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
79 | BG_079 | User Management | User List | Role, Status are distrubing view. | 2025-08-25 | Internal | Medium | Medium | Functional |  | Resolved | Shekar | Resolved | [8 empty] | TRUE
80 | BG_080 | User Management | Role Permission | The Delivery page is missing from the Role Permission page. Even without assigning the role permission, the Manufacturing Rep is able to access the role upon login. | 2025-08-25 | Internal | Medium | Medium | Functional | Resolved | Resolved | Shekar | Resolved | [8 empty] | TRUE
81 | BG_081 | User Management | Role Permission | Nameaing conventions was missing (ex:- port in side bar but port master in permission matrics). | 2025-08-25 | Internal | Critical | Medium | Functional | Resolved | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
82 | BG_082 | User Management | Permission Matrix | Nameing convention missing in the roles page matrix. Port in the side nav and port master in the role permission matrix. | 2025-08-25 | Internal | Critical | Medium | Functional | Resolved | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
83 | BG_083 | Master | Permission Matrix | LME in permission matrix and nav. LME price in the permission matrix. | 2025-08-25 | Internal | Critical | Medium | Functional |  | Resolved | Shekar | Resolved | [8 empty] | TRUE
84 | BG_084 | User Management | Permission Matrix | The Delivery page is missing from the Role Permission page. Even without assigning the role permission, the Manufacturing Rep is able to access the role upon login. | 2025-08-25 | Internal | Critical | Medium | Functional |  | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
85 | BG_085 | Master | Customer Category | Customer Category is not working. | 2025-08-25 | Internal | Critical | Medium | Functional | 2025-09-12 | Resolved | Praneeth | Resolved | [8 empty] | TRUE
86 | BG_086 | Master | Payment terms | Payment terms delete is not working. | 2025-08-25 | Internal | Critical | Medium | Functional | 2025-09-12 | Resolved | Praneeth | Resolved | [8 empty] | TRUE
87 | BG_087 | Master | Delivery Master. | Getting wrong data in the front end. In ID place getting name, name place getting ID. - Delivery Master. | 2025-08-25 | Internal | Critical | Medium | Functional |  | Resolved |  | Resolved | [8 empty] | TRUE
88 | BG_088 | Master | port master | Edit is not working in the port master. | 2025-08-25 | Internal | Critical | Medium | Functional | 2025-09-12 | Resolved | Praneeth | Resolved | [8 empty] | TRUE
89 | BG_089 | Master | Manufacturing rep commission | Manufacturing rep commission totally not working. | 2025-08-25 | Internal | Critical | Medium | Functional |  | Resolved | Kishore | Resolved | [8 empty] | TRUE
90 | BG_090 | Master | Add Customer VA Percentage. | While filling the data in the Conductor Type getting the error in the Add Customer VA Percentage. | 2025-08-25 | Internal | Critical | Medium | Functional |  | Resolved | Kishore | Resolved | [8 empty] | TRUE
91 | BG_091 | Master | Customer VA Percentages. | Add, edit, delete not working in the Customer VA Percentages. | 2025-08-25 | Internal | Critical | Medium | Functional | 2025-09-12 | Resolved | Praneeth | Resolved | [8 empty] | TRUE
92 | BG_092 | Master | Product material | Product material cost not working totally. | 2025-08-25 | Internal | Critical | Medium | Functional |  | Resolved | RK | Resolved | [8 empty] | TRUE
93 | BG_093 | Master | LME prize | LME prize getting error while entering. | 2025-08-25 | Internal | Critical | Medium | Functional |  | Resolved | RK | Resolved | [8 empty] | TRUE
94 | BG_094 | Master | Pricing Configurations | Pricing configuration getting error, edit, delete not working. | 2025-08-25 | Internal | Critical | Medium | Functional |  | Resolved | RK | Resolved | [8 empty] | TRUE
95 | BG_095 | Product Master | Product Category. | Taking duplicate rows. Delete not working - Product Category. | 2025-08-25 | Internal | Critical | Medium | Functional | 2025-09-12 | Resolved | praneeth | Resolved | [8 empty] | TRUE
96 | BG_096 | Product Master | Customer type | Add not working, edit - Conductor Type. | 2025-08-25 | Internal | Critical | Medium | Functional | Resolved | Resolved | Subbu | Resolved | [8 empty] | TRUE
97 | BG_097 | Product Master | Voltage Grade. | Add Voltage Grade not working - Voltage Grade. | 2025-08-25 | Internal | Critical | Medium | Functional | Resolved | Resolved | Subbu | Resolved | [8 empty] | TRUE
98 | BG_098 | Product Master | Insulation | Insulation total different. | 2025-08-25 | Internal | Critical | Medium | Functional | Resolved | Resolved | Subbu | Resolved | [8 empty] | TRUE
99 | BG_099 | Product Master | Insulation Level page. | Add, edit insulation level not working - Insulation Level page. | 2025-08-25 | Internal | Critical | Medium | Functional | Resolved | Resolved | Subbu | Resolved | [8 empty] | TRUE
100 | BG_100 | Product Master | Outer Jacket. | Add, edit Outer Jacket is not working - Outer Jacket. | 2025-08-25 | Internal | Critical | Medium | Functional | Resolved | Resolved | Subbu | Resolved | [8 empty] | TRUE
101 | BG_101 | Product Master | UL Certification. | Add Certification, edit Certification - UL Certification. | 2025-08-25 | Internal | Critical | Medium | Functional | Resolved | Resolved | Subbu | Resolved | [8 empty] | TRUE
102 | BG_102 | Product Master | Flame Test. | Add, edit not working Flame Test - Flame Test. | 2025-08-25 | Internal | Critical | Medium | Functional | Resolved | Resolved | Subbu | Resolved | [8 empty] | TRUE
103 | BG_103 | Product Master | Product. | When entering 'q' in the product search box complete page was missing - Product. | 2025-08-25 | Internal | Critical | Medium | Functional |  | Resolved |  | Resolved | [8 empty] | TRUE
104 | BG_104 | User Management | Edit User | Edit functionality is not working on the Edit User page. | 2025-09-05 | Internal | Critical | Critical | Functional |  | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
105 | BG_105 | Product Master | Product | Product search is not working. | 2025-09-05 | Internal | Medium | Medium | Functional | 2025-09-12 | Resolved | Praneeth | Resolved | Fixed | [7 empty] | TRUE
106 | BG_106 | Product Master | Product | When clicking the arrow button filter, it behaves unexpectedly (moves in the wrong direction). | 2025-09-05 | Internal | Medium | Medium | Functional | 2025-09-12 | Resolved | Praneeth | Resolved | [8 empty] | TRUE
107 | BG_107 | Product Master | Product | If a product is added to a list of 2,000 records, how will the user search for the new record? | 2025-09-05 | Internal | Medium | Medium | Functional |  | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
108 | BG_108 | Master | VA percentage | When a product is added in the Product Category, it is not reflected in the VAT percentage and does not appear in the dropdown. | 2025-09-05 | Internal | Medium | Medium | Functional |  | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
109 | BG_109 | Master | port master | While adding a record in the Port section, there are 5 fields, but the Port grid shows only 4 fields. | 2025-09-05 | Internal | Medium | Medium | Functional | 2025-09-12 | Resolved | Shekar | Resolved | [8 empty] | TRUE
110 | BG_110 | Customer | Customer | APAR executive issues are pending.in the customer page | 2025-09-05 | Internal | Medium | Medium | Functional |  | Resolved | Sumukesh | Resolved | No Issue Found | [7 empty] | TRUE
111 | BG_111 | Customer | Customer | Admin customer issues are pending.in the customer page | 2025-09-05 | Internal | Medium | Medium | Functional |  | Resolved | Sumukesh | Resolved | No Issue Found | [7 empty] | TRUE
112 | BG_112 | User Management | Add User | While rejecting a mini user, the status still remains active instead of being updated. | 2025-09-05 | Internal | Medium | Medium | Functional |  | Resolved | Sumukesh | Resolved | No Issue Found | [7 empty] | TRUE
113 | BG_113 | User Management | User List | once the mini user created making status as (aprove/ reject). | 2025-09-05 | Internal | Medium | Medium | Functional |  | Resolved | Sumukesh | Resolved | No Issue Found | [7 empty] | TRUE
114 | BG_114 | User Management | User List | what if we create the reject email, want to cretate the user (or) denined. | 2025-09-05 | Internal | Medium | Medium | Functional |  | Resolved | Sumukesh | Resolved | If user is denie, He would able to access the application | [7 empty] | TRUE
115 | BG_115 | User Management | User List | once if we reject the mini user. want the option of Approve onthoer time. | 2025-09-05 | Internal | Medium | Medium | Functional |  | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
116 | BG_116 | User Management | Edit User | once mini user was created by default Manufacturing Rep will place in to drop down. don't want to change. (read only) | 2025-09-05 | Internal | Medium | Medium | Functional |  | Resolved | Praneeth | Resolved | Not an Issue | [7 empty] | TRUE
117 | BG_117 | User Management | User List | Once the role reject the in-active switch make as OFF. | 2025-09-05 | Internal | Medium | Medium | UI |  | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
118 | BG_118 | User Management | User List | Mini user - better naming | 2025-09-05 | Client | Medium | Medium | Functional |  | Resolved | Praneeth | Resolved | [8 empty] | TRUE
119 | BG_119 | User Management | Email | Direct verify without code – click on verify email - directly to change password. | 2025-09-05 | Client | Medium | Medium | Functional |  | Resolved | Praneeth | Resolved | [8 empty] | TRUE
120 | BG_120 | User Management | Email | Template and email for verification/automation improvise design | 2025-09-05 | Client | Medium | Medium | Functional |  | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
121 | BG_121 |  |  | Single product page – Details page | 2025-09-05 | Client | Medium | Medium | Functional |  | Resolved | Shekar/Praneeth | Resolved | [8 empty] | TRUE
122 | BG_122 | User Management | Role Permission | Main menu and sub menu in role matrix | 2025-09-05 | Client | Medium | Medium | Functional |  | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
123 | BG_123 |  |  | Add separate page before quote creation page – exactly same as product matrix | 2025-09-05 | Client | Medium | Medium | UI |  | Resolved | Shekar | Resolved | [8 empty] | TRUE
124 | BG_124 |  |  | View products only with the filters data and should be similar to quotations listing page also the single product page can be opened from this product listing page. | 2025-09-05 | Client | Medium | Medium | UI |  | Resolved | Shekar | Resolved | [8 empty] | TRUE
125 | BG_125 | User Management | Add/Edit User | Manufacturing rep login - add mini user – manufacturing rep auto tagged and shown the non-editable auto tagged manufacturing rep’s name. | 2025-09-05 | Client | Medium | Medium | Functional |  | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
126 | BG_126 |  |  | User role management - keep separate status for pending approval (Mini user) and pending verification (for all users) | 2025-09-05 | Client | Medium | Medium | Functional |  | Resolved | Kishore | Resolved | [8 empty] | TRUE
127 | BG_127 |  |  | Status -> Active/ In active | 2025-09-05 | Client | Medium | Medium | Functional |  | Resolved | Shekar | Resolved | [8 empty] | TRUE
128 | BG_128 | User Management | User List | Approval status -> Status | 2025-09-05 | Client | Medium | Medium | Functional |  | Resolved | Shekar | Resolved | [8 empty] | TRUE
129 | BG_129 | Master |  | Column width reduce and make it visible on a same page for Sales rep commission page | 2025-09-05 | Client | Medium | Medium | UI |  | Resolved | Shekar | Resolved | [8 empty] | TRUE
130 | BG_130 |  |  | Default 3.5% sales rep commission newly added | 2025-09-05 | Client | Medium | Medium | Functional |  | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
131 | BG_131 |  |  | Remove the destination port from the enquiry form when creating the quote when user selects FOB. | 2025-09-05 | Client | Medium | Medium |  |  | Resolved | Kishore | Resolved | [8 empty] | TRUE
132 | BG_132 |  |  | Email and phone number unique per user. | 2025-09-05 | Client | Medium | Medium |  |  | Resolved | RK | Resolved | Email id is unique | [7 empty] | TRUE
133 | BG_133 | Customer |  | Address – remove linkage from zipcodes and keep only dropdowns each for city, state and zipcodes & auto fill from browser | 2025-09-05 | Client | Medium | Medium |  |  | Resolved | Shekar | Resolved | [8 empty] | TRUE
134 | BG_134 |  |  | Shipping not mandatory, only billing mandatory – new customer addition form | 2025-09-05 | Client | Medium | Medium |  |  | Resolved |  | Resolved | [8 empty] | TRUE
135 | BG_135 | Customer |  | Customer listing page also changes – combination of report + listing with expand/collapse columns | 2025-09-05 | Client | Medium | Medium | Functional |  | Resolved | RK/Shekar | Resolved | [8 empty] | TRUE
136 | BG_136 |  |  | Provide a link to the quote from all the quote numbers across all the pages | 2025-09-05 | Client | Medium | Medium | Functional |  | Resolved | Kishore | Resolved | [8 empty] | TRUE
137 | BG_137 |  |  | Quote number – logic create unique code during the manufacturing rep creation and add It in the quote number. | 2025-09-05 | Client | Medium | Medium |  |  | Resolved | RK/Kishore | Resolved | [8 empty] | TRUE
138 | BG_138 |  |  | Revision number – starts with version instead of revision like v1 (version 1) | 2025-09-05 | Client | Medium | Medium |  |  | Resolved | RK | Resolved | [8 empty] | TRUE
139 | BG_139 |  |  | Add EPC Contractor dropdown from the customer list (mandatory) & End customer (free text field) in the enquiry page when generating the quotation. | 2025-09-05 | Client | Medium | Medium |  |  | Resolved | RK/Kishore | Resolved | [8 empty] | TRUE
140 | BG_140 |  |  | Sector show Dropdown all options again – enquiry page when generating the quotation | 2025-09-05 | Client | Medium | Medium | Functional |  | Resolved | Kishore | Resolved | [8 empty] | TRUE
141 | BG_141 | Product Master |  | Product selection page – “All Categories” to be in placeholder. | 2025-09-05 | Client | Medium | Medium | Functional |  | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
142 | BG_142 |  |  | XHHW-2 as default category for product selection page | 2025-09-05 | Client | Medium | Medium | Functional |  | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
143 | BG_143 |  |  | Make the product selection page compact and reduce space wastage | 2025-09-05 | Client | Medium | Medium | UI |  | Resolved | Shekar | Resolved | [8 empty] | TRUE
144 | BG_144 | Quotation |  | Change Quotation Page heading to Quotation Summary page | 2025-09-05 | Client | Medium | Medium | Functional |  | Resolved | Kishore | Resolved | [8 empty] | TRUE
145 | BG_145 | Product Master | Products | All validations are missing while updating the product information | 2025-09-17 | Internal | High | High |  |  | Resolved | Sumukesh | Resolved | No validation for all records | [7 empty] | TRUE
146 | BG_146 | User Management | Role | what happens when a role is deactivated to users who have that role? | 2025-09-18 | Client | High | High | Functional |  | Resolved | Sumukesh | Resolved | User will not able to login | [7 empty] | TRUE
147 | BG_147 | Customer | Add Customer | Add new customer – default keep street empty | 2025-09-05 | Client | Medium | Medium | Functional |  | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
148 | BG_148 | Product Master |  | Details page alignment on top back button |  | Internal |  |  | UI |  | Resolved | Shekar | Resolved | [8 empty] | TRUE
149 | BG_149 | User Management | OTP | otp issue. | 2025-09-22 | Internal |  |  | Functional |  | Resolved | RK | Resolved | [8 empty] | TRUE
150 | BG_150 | User Management | Role Permission | Analysis and Reporting getting in all pages | 2025-09-24 | Internal |  |  | Functional |  | Resolved | Praneeth | Resolved | [8 empty] | TRUE
151 | BG_151 | Customer |  | On the customer page, the Next button was clicking twice and going to the next page | 2025-09-24 | Internal |  |  | Functional |  | Resolved | Kishore | Resolved | [8 empty] | TRUE
152 | BG_152 | Quotation | Create Quotation | Some blue patch in the place of END coustomer, Job Name drop down. | 2025-09-24 | Internal |  |  | UI |  | Resolved | Shekar | Resolved | [8 empty] | TRUE
153 | BG_153 | User Management | Role Permission | Role permission Bulk error. |  | Internal |  |  | Functional |  | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
154 | BG_154 | User Management | Role Permission | When we are click on the role permissions check box rest of 3 boxes are checking | 2025-09-24 | Internal |  |  | Functional |  | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
155 | BG_155 | User Management | Role Permission | Duplicate records are adding in the role permissions | 2025-09-24 | Internal |  |  | UI |  | Resolved | Sumukesh | Resolved | [8 empty] | TRUE
156 | BG_156 | Settings | Schedular Configrations | Scheduler Management | 2025-09-25 | Internal |  |  | RK / Praneeth |  | Resolved | RK / Praneeth | Resolved | In Product view ie is penidng
157 | BG_157 | Master Data | Lme Price | LME Price (decending order) | 2025-09-25 | Internal |  |  | Shekar |  | Resolved |  | Resolved
158 | BG_158 | Master Data | Lme Price | Date time AL Price, CU price, AL (LB) , CU(LB) | 2025-09-25 | Internal |  |  | Shekar |  | Resolved |  | Resolved
159 | BG_159 | Master Data | Lme Price | Remove the LME price history - remove from DB | 2025-09-25 | Internal |  |  | Shekar |  | Resolved | Shekar | Resolved
160 | BG_160 | Settings | Schedular Configrations | Add Schedular Config, Schedular tracking menu in the settings | 2025-09-25 | Internal |  |  | Shekar |  | Resolved | Shekar | Resolved
161 | BG_161 | Settings | Schedular Configrations | Schedular Tracking - Jobname Start date Start time End date End time Status (S/F) | 2025-09-25 | Internal |  |  | Shekar |  | Resolved | Kishore | Resolved
162 | BG_162 | Quotation Managment | Quotation Managment | Quotation Preview - If FOB selected, Show selected Columns | 2025-10-06 | Internal |  |  | Kishore |  | Resolved | Kishore | Resolved
163 | BG_163 | Quotation Managment |  | Cart and delete scenario - Generate Quotation | 2025-10-06 | Internal |  |  | Kishore |  | Resolved | Kishore | Resolved
164 | BG_164 |  |  | Customer already exists condition and show warning message | 2025-10-06 | Internal |  |  | Kishore |  | Resolved | Functional | Resolved
165 | BG_165 | Quotation Managment | Product selcetion | Multiple Add to cart - messages - removal | 2025-10-06 | Internal |  |  | Functional |  | Resolved | Kishore | Resolved
166 | BG_166 | Products |  | Products and Accounts icons are same | 2025-10-06 | Internal |  |  |  |  | Resolved | Shekar | Resolved
167 | BG_167 | Products | Products | In Products page, Product category Filter with Lazy loading is not working. | 2025-10-06 | Internal |  |  | Functional |  | Resolved | Praneeth/Shekar | Resolved
168 | BG_168 |  |  | I think you can remove heading title for space constraint | 2025-10-06 | Internal |  |  |  |  | Resolved | Shekar | Resolved
169 | BG_169 |  |  | Please implement header collapse when scroll to bottom | 2025-10-06 | Internal |  |  | UI |  | Resolved | Shekar | Resolved | Release 1B
170 | BG_170 | Account | Accounts List | We have changed Customers to Accounts, But Still I see Account View Details page as Customer keyword. Pls change In accounts List page | 2025-10-06 | Internal |  |  |  |  | Resolved | Shekar | Resolved
171 | BG_171 | Product Master | Produts | Searching Productname in search bar not working | 2025-10-07 | Internal |  |  | Functional |  | Resolved | Sumukesh | Resolved
172 | BG_172 |  |  | Productslist view change the link to Products - link need to change | 2025-10-07 | Internal |  |  |  |  | Resolved | Shekar | Resolved
173 | BG_173 | side Nav Bar | Master Data | manufacturing rep icon and VA percentage nav bar icons are same..(%) | 2025-10-10 | Internal |  |  | UI |  | Resolved | Shekar | Resolved
174 | BG_174 | Quotation Managment | Edit Quotation | All product Category dropdown is merging. | 2025-10-07 | Internal |  |  | Shekar |  | Resolved |  | Resolved
175 | BG_175 | Quotation Managment | cart & commerial | "You have unsaved changes in quantities. Please recalculate to see updated prices". can we make alert bright to grab user attention. | 2025-10-07 | Internal |  |  | UI |  | Not an issue | Shekar | Not an issue
176 | BG_176 | Product Master | Product list View | in the product view page CT rated was not clearly visible, and in the Logistics & packaging(tab) Minimum Order Quantity is not visible correctly. | 2025-10-07 | Internal |  |  | UI |  | Resolved | Shekar | Resolved
177 | BG_177 | Account | Add Account | creating the account with Manfacturing rep. but getting the manufacturing rep is manually in the dropdown but want it dynamic. | 2025-10-07 | Internal |  |  | Functional |  | Resolved | Kishore | Resolved
178 | BG_178 | Accounts | Quotationhistory | getting [object Object] in the customer view page. | 2025-10-07 | Internal |  |  |  |  | Resolved |  | Resolved
179 | BG_179 | Quotation Managment | Quotation | quotation management model quotations status filter is not working for expiry status. | 2025-10-07 | Internal |  |  | Functional |  | Resolved | Kishore | Resolved
180 | BG_180 | Account | Products | Presently its displaying as a static page, we are not getting dynamic products | 2025-10-07 | Internal |  |  | Functional |  | Resolved | Praneeth | Open | Release 1B
181 | BG_181 | Quotation Managment | Product selcetion | select Items and add to cart click next then remove all items in cart, Next Button is displaying in cart Page , It will directlly redirecting to the cart and commericial without items | 2025-10-08 | Internal |  |  | Functional |  | Resolved | Kishore | Resolved
182 | BG_182 | Quotation Managment | cart & commerial | Served Forms and Inco terms labels Overrriding | 2025-10-08 | Internal |  |  | UI |  | Resolved | Shekar | Resolved
183 | BG_183 | UserMangment | Role Permission | Rename Customer to Accounts in permission Matrix | 2025-10-08 | Internal |  |  | UI |  | Resolved | Sumukesh | Resolved
184 | BG_184 | Header | Top Header | Apar inside sales role AL & Cu values are missing. | 2025-10-08 | Internal |  |  | UI |  | Resolved | Shekar | Resolved | [7 empty] | Subbu
185 | BG_185 | Usermanagment | Permission Matrics/ Product- Sub Catagories. | give permission to view the products but getting the permission to delete, edit and add. | 2025-10-09 | 2025-10-09 |  |  | Functional |  | open | Praneeth | Open | [7 empty] | Subbu
186 | BG_186 | Nav bar | Nav bar | same icons in the nav bar for analystics & Reports | 2025-10-09 | Internal |  |  | UI |  | Not an issue | Shekar | Not an issue | [7 empty] | Subbu
187 | BG_187 | Accounts | Account Profile | Account Screens - product history and quote history Search is missing | 2025-10-09 | Internal |  |  | Functional |  | Resolved | Shekar | Resolved
188 | BG_188 | MasterData | rep Commision | For the user's Doesnt have any s.no or Id's | 2025-10-09 | Internal |  |  | UI |  | Not an issue |  | Resolved
189 | BG_189 |  |  | If product selection page donesnt have any ites, after deleting the products in the cart popup, i can able to click on next and able to view the Cart commercial page , But in general senerio its working fine | 2025-10-09 | Internal |  |  | Functional |  | Resolved | Kishore | Resolved
190 | BG_190 | AparInside sales | Account | When iam trying to create New Account redirecting to Dashboard / If there is no permission for the add Disable the addAccount Button | 2025-10-09 | Internal |  |  | Functional |  | Resolved | Praneeth | Resolved
191 | BG_191 |  |  | Delivery master Schedular | 2025-10-09 | Internal |  |  | Functional |  | Not an issue | Jay | Not an issue
192 | BG_192 | Quotation Managment | Product selection | Select Product in Production selction Page add product to the cart, products get refreshed and Products are coming from the Starting . But not From the Previous selecction Product | 2025-10-11 | Internal |  |  | Functional |  | Not an issue | Sumukesh | Not an issue
193 | BG_193 | Accounts | Quotationhistory | Date Format need to change MM/DD/YR | 2025-10-11 | Internal |  |  | Functional |  | Resolved | Shekar | Resolved
194 | BG_194 | Accounts | Quotationhistory | "APAR/AT/1025/00068-v1 " This is a Approved Quotation, When check in Accounts >> Quotation History >> click above quote id >>Quotation summery is empty | 2025-10-11 | Internal |  |  | Functional |  | Resolved | Praneeth | Resolved
195 | BG_195 | Accounts | Quotationhistory | Account Screens - product history and quote history Search is missing | 2025-10-11 | Internal |  |  | Functional |  | Resolved | Praneeth | Resolved
196 | BG_196 | Accounts | Quotationhistory | Total value Getting $0 in quotation History | 2025-10-11 | Internal |  |  | Functional |  | Resolved | Praneeth | Resolved
197 | BG_197 | Accounts | Add account | Manufature rep : Adding New Account in Accounts >> Account Owner remove Dropdown need to autofill the Name , need to readOnly | 2025-10-13 | Internal |  |  | Functional |  | Resolved | Kishore | Resolved | Fixed in release-1B
198 | BG_198 | Settings | Submenus | Setting nav >> Icons need to change for Schedular tracking ,auditlog,Terms and conditions | 2025-10-13 | Internal |  |  | Ui |  | open | Shekar | Open
199 | BG_199 | Analyticsand Reporting | Submenus | Unable to select Date input fields In all Settings sub menus | 2025-10-13 | Internal |  |  | UI |  | Resolved | Praneeth | Resolved
200 | BG_200 | Analyticsand Reporting | QuotationStatus | filters are not Working as expected | 2025-10-13 | Internal |  |  | Ui |  | open |  | Open
201 | BG_201 | UserMangment | AddNew user | manufacure rep : select Role is getting only readonly for this user , manufature rep doesnt have chance to create aparInside Sales | 2025-10-13 | Internal |  |  | Functional |  | Resolved |  | Resolved
202 | BG_202 | Analytics &Reports | Sales summery | Approved Quotes field are Getting 0 for all users | 2025-10-13 | Internal |  |  | Functional |  | Resolved |  | Resolved
203 | BG_203 | Master Data | Delivery | Add Delivery and Update delivery notworing In Delivery Page | 2025-10-14 | Internal |  |  | Functional |  | Resolved | Sumukesh | Re-open
204 | BG_204 | Quotation Managment | cart and commercial | 1. Add Products to the cart check the Total Prices of the Products with Different Stocks 2. use same products and qty Make india stock and DDP - recalclate Note values >> Go to Previous >> Click Next >> price is Different >> Those are Us Stock Values | 2025-10-15 | Internal |  |  | Functional |  | Resolved | Kishore | Resolved
205 | BG_205 | Quotation Managment | Product selcetion | 1. Add any Product to cart and >> remove fromt he cart >> again add the same Product to cart | 2025-10-15 | Internal |  |  | Functional |  | Resolved | Kishore | Resolved
206 | BG_206 | Quotation Managment | cart and commercial | When u add Product to the cart make india fob dont recalculate >> previous >> click next >> "recalculate Button and generae quote Button disabled " | 2025-10-16 | Internal |  |  | Functional |  | Resolved | Kishore | Resolved
207 | BG_207 | Products | Update Product | While Updating the Existing Product getting "failed to Update",Delting Product is not working | 2025-10-30 | Internal |  |  | Functional |  | Resolved | Sumukesh | Re-open
208 | BG_208 | Quotation Managment | Qutations | Pagination Issue >> When u are in 41-50 page Select any filter Quotations are apraing in last Page , It must have to start Between the 1-10 | 2025-10-17 | Internal |  |  | Functional |  | Resolved | Kishore | Resolved
209 | BG_209 | Prducts | Products | Images getting Small sizes in Products Pages categories :MV EPR,MV TR-XLPE,RHH/RHW-2,UD,UDR | 2025-10-17 | Internal |  |  | Functional |  | Resolved | Shekar/Kishore | Resolved
210 | BG_210 | Manufacture rep | users | Edit >> Current Manufacturing Rep is not available now. Please change the manufacturing representative.>> Pop-up message appearing for users while editing | 2025-10-17 | Internal |  |  | Functional |  | Resolved | Praneeth | Resolved
211 | BG_211 | Manufacture rep | users | Only Manufature rep lniked users Must appeard in the userlist ,Not all Miniusers | 2025-10-17 | Internal |  |  | Functional |  | Resolved | Praneeth | Resolved
212 | BG_212 | Iside Sales | users | Inside sales are not dispalying They must have to Display linked Manufature reps | 2025-10-17 | Internal |  |  | Functional |  | Resolved | Praneeth | Re-open
213 | BG_213 | Apar sales executive | Users | Display Only MF and IS linked to their Particular AparSales Executive | 2025-10-17 | Internal |  |  | Functional |  | Resolved | Praneeth | Resolved
214 | BG_214 | Usermanagment | Users | Restrict the roles Dropdown as per the user ASE can ahve to see the dropdown only MF,Inside sales Only .It is Displayng Admin,AparSalesexecutive also | 2025-10-17 | Internal |  |  | Functional |  | Resolved | Praneeth | Resolved
215 | BG_215 | Usermanagment | AparSalesExecutive | AparSalesExecutive can't view his users.. MR and Inside sales | [6 empty] | Open | Praneeth | Resolved
216 | BG_216 | Usermanagment | manuacturerep | Add Back Button in ViewProfile Page | 2025-10-18 | Internal |  |  | Functional |  | Resolved | Praneeth | Re-open
217 | BG_217 | Products | Products | All Products Drop down Filter is Not working ,Comapre with XHHW-2 Product | 2025-10-18 | Internal |  |  | Functional |  | Resolved | Shekar/Kishore | Resolved
218 | BG_218 | Products | Products | None Of Products Doesn't have the Tech sheet's |  | Internal |  |  | Functional |  | Resolved | Sumukesh | Resolved
219 | BG_219 | Accounts | Quotation Summery | BIlling Adress and Shipping Adress Getting Null In Quotation summery For Approved Quotation | 2025-10-22 | Internal |  |  | Functional |  | Resolved | Sumukesh/Kishore | Resolved
220 | BG_220 | Accounts | Quotation Summery | APAR/KK/1025/00027-v1 This is a Approved Quotaion>> click on This Quotation Account name >> Go to quotation summery >>check the same Quotation getting values Null | 2025-10-22 | Internal |  |  | Functional |  | Resolved | Praneeth | Resolved
221 | BG_221 | Accounts | Account Details | Click Address Details Drop down Getting Null For "SolarEdgeSolution" | 2025-10-22 | Internal |  |  | Functional |  | Resolved | Sumukesh/Kishore | Resolved
222 | BG_222 | Accounts | Quotation history | Quotation Status colors need to change based On their Status | 2025-10-22 | Internal |  |  | Functional |  | Resolved | Praneeth/Shekar | Resolved
223 | BG_223 | Quotation | cart and comercial | Billing and Shiping adress are null | 2025-10-22 | Internal |  |  | Functional |  | Resolved | Sumukesh/Kishore | Resolved
224 | BG_224 | Quotation | Quotation | 5 times repeated calculations - Code clean up | 2025-10-22 | Internal | Functional | Open | Functional |  | Open | Sumukesh | Open
225 | BG_225 | Analytics &Reports | Sales rep | AllSales rep and Allstatus Label are not Displaying in input field | [6 empty] | open |  | open
226 | BG_226 | Analytics &Reports | Sales rep summery | Grid view Approved Quotes are oming 0 | [6 empty] | open |  | open
227 | BG_227 | Analytics &Reports | Quotation status | All salesrep label , All Product catogery labes are not Displying | [6 empty] | open |  | open
228 | BG_228 | Analytics &Reports | Quotation status | kanban view Ascending and descending Ordeer is not working | [6 empty] | open |  | open
229 | BG_229 | Analytics &Reports | Sales Commision reports | Filters and All Labels are not Working | [6 empty] | open |  | open
230 | BG_230 | Analytics &Reports | ProductSummery reports | All labes and Filters and quotation Value getting NAN | [6 empty] | open |  | open
231 | BG_231 | Analytics &Reports | Customer summery | pagination Arrow is Not displaying | [6 empty] | open |  | open

## Client Issues
S.No | Issue Description | Date Identified | Reported By | Type | Assigned To | Start Date | Fixed On | Dev Status | Qa Status | Release Type | Issuse Raised By | Raised Date | Dev Comments | Client Comments
1 | One product with different reel length not working in cart page | 2025-09-12 | Client | Functional | Sumukesh |  | 2025-09-18 | Resolved | Resolved | Release 1A
2 | Reel length not reflecting when selected in product selection | 2025-09-12 | Client | Functional | Sumukesh |  | 2025-09-18 | Resolved | Resolved | Release 1A
3 | Copy quote or replicate quote from existing quote to alter the qty/reel length/product and generate a new quote | 2025-09-12 | Client | Functional | RK/Kishore | 2025-10-08 | 2025-10-08 | Resolved | Resolved | Release 1B
4 | Delete product from the cart | 2025-09-12 | Client |  | RK/Kishore |  |  | Resolved | Resolved | Release 1A
5 | Change Customer to Customers | 2025-09-12 | Client | Functional | Shekar |  | 2025-09-19 | Resolved | Resolved | Release 1A
6 | Change Product Master to just Products | 2025-09-12 | Client | Functional | Shekar |  | 2025-09-19 | Resolved | Resolved | Release 1A
7 | Change subcategory product to Products and use same product page as quotation management | 2025-09-12 | Client | Functional | Shekar |  | 2025-09-19 | Resolved | Resolved | Release 1A
8 | In Users – status filter wrongly shows active inactive add active filter | 2025-09-12 | Client | Functional | Praneeth |  | 2025-09-19 | Resolved | Resolved | Release 1A
9 | In new customer what does Account Domain Name * | 2025-09-12 | Client | Functional | Shekar |  | 2025-09-19 | Resolved | Resolved | Release 1A
10 | In Quote Status change Save as Draft to Draft | 2025-09-12 | Client | Functional | Shekar |  | 2025-09-19 | Resolved | Resolved | Release 1A
11 | Add filters for quote management | 2025-09-12 | Client | Functional | Kishore |  | 2025-09-18 | Resolved | Resolved | Release 1A
12 | Change default category to All Products when clear filter it should go to all products and introduce pagination, load up to 10 (lazy loading) | 2025-09-12 | Client | Functional | RK/Sumukesh |  |  | Resolved | Resolved | Release 1B
13 | Reduce space between arrow and colour button in quote | 2025-09-12 | Client | Functional | Shekar |  | 2025-09-19 | Resolved | Resolved | Release 1A
14 | Reel Length selector not working | 2025-09-12 | Client | Functional | Sumukesh |  | 2025-09-18 | Resolved | Resolved | Release 1A
15 | Pop out cart changer not working | 2025-09-12 | Client | Functional | Sumukesh |  | 2025-09-18 | Resolved | Resolved | Release 1A
16 | Add next button to bottom of pop out cart | 2025-09-12 | Client |  | Kishore |  |  | Resolved | Resolved | Release 1A
17 | Qty changer in cart page not working | 2025-09-12 | Client | Functional | Sumukesh |  | 2025-09-18 | Resolved | Resolved | Release 1A
18 | All menu and submenu icons need to update | 2025-09-12 | Client | Functional | Shekar |  | 2025-09-19 | Resolved | Resolved | Release 1A
19 | Hamburger menu click open the side bar | 2025-09-12 | Client | Functional | Kishore |  | 2025-09-18 | Resolved | Resolved | Release 1A
20 | In product selection page, Left side all filters has to display in Ascending order. | 2025-09-18 | Client | Functional | RK |  | 2025-09-22 | Resolved | Resolved | Release 1A
21 | Add to cart: same product reel length and color were added.. Quantity has to keep on addition to the product. | 2025-09-18 | Client | Functional | Sumukesh |  | 2025-09-23 | Resolved | Resolved | Release 1A
22 | Duplicate reelLengths are displaying while choosing reel length in dropdwon. | 2025-09-18 | Client | Functional | Sumukesh |  | 2025-09-18 | Resolved | Resolved | Release 1A
23 | Dashboard Tile cards UI spacing issue | 2025-09-18 | Client | Functional | Shekar |  | 2025-09-19 | Resolved | Resolved | Release 1A
24 | For Super admin as to have Products Master Menu and Sub menus as products and all sub product filters. | 2025-09-18 | Client | Functional | Sumukesh |  | 2025-09-18 | Resolved | Resolved | Release 1A
25 | Where as for other roles, Menu has to assign Products and that page has to come as Product selection page. | 2025-09-18 | Client | Functional | Shekar |  | 2025-09-19 | Resolved | Resolved | Release 1A
26 | Tech sheet and Quotation PDF has to downloadable from application. | 2025-09-18 | Client | Functional | Sumukesh |  | 2025-09-23 | Resolved | Resolved | Release 1A |  |  | Quotation PDF is completed, Tech sheet is pending | Need S3 Bucket
27 | Quotation PDF suggested changes has to reflect in next build. | 2025-09-18 | Client | Functional | Sumukesh |  | 2025-09-18 | Resolved | Resolved | Release 1A
28 | Account Website Name rename as Account Website/Website | 2025-09-18 | Client | Functional | Shekar |  | 2025-09-19 | Resolved | Resolved | Release 1A
29 | Confirmation required on Whether to use Customers or Account - Please confirm | 2025-09-18 | Client | Functional | Aditya |  |  | Resolved | Resolved | Release 1A
30 | Generate Quotation - Change it to Approved status - Email with attachment | 2025-09-18 | Client | Functional | RK/Sumukesh |  | 2025-09-19 | Resolved | Resolved | Release 1A
31 | "https://prd.aparusa.com/" should take you to the dashboard or the login page if not logged in settings button on dashboard doesnt do anything | 2025-09-18 | Client | Functional | Kishore |  | 2025-10-30 | Resolved | Open | Release 1B
32 | Unable to edit profile page | 2025-09-18 | Client | Functional | Praneeth |  |  | Resolved | Resolved | Release 1A |  |  | based on the users list edit we need to redirect the same
33 | when you clock outside of the account menu on the right or on any of the menu options it should close | 2025-09-18 | Client | Functional | Shekar |  | 2025-09-19 | Resolved | Resolved | Release 1A
34 | headline not showing in users page until you scroll up try to fit users horizontally in the page | 2025-09-18 | Client | Functional | Kishore |  |  | Resolved | Resolved | Release 1A
35 | What happens when a role is deactivated to users who have that role? |  |  |  | Kishore |  |  | Resolved | Resolved | Release 1A |  |  | Users can't able to login, Super admin has to reassign a new role to all users
36 | All Categories not working for all products | 2025-09-18 | Client | Functional | Sumukesh |  | 2025-09-30 | Resolved | Resolved | Release 1A |  |  | Getting performance issues
37 | Color options only showing black or white Reel Length duplicate options showing | 2025-09-18 | Client | Functional | Sumukesh |  | 2025-09-22 | Resolved | Resolved | Release 1A
38 | Going from cart page back to previous page empties the cart- getting error falied to upload | 2025-09-18 | Client | Functional | Kishore |  |  | Resolved | Resolved | Release 1A
39 | When changing served from or Inco Terms getting this error | 2025-09-18 | Client | Functional | RK/Sumukesh |  | 2025-09-19 | Resolved | Resolved | Release 1A
40 | Download PDF not working | 2025-09-18 | Client | Functional | Sumukesh |  | 2025-09-19 | Resolved | Resolved | Release 1A
41 | Quotation Status not updating on quote creation | 2025-09-18 | Client | Functional | Kishore |  | 2025-09-19 | Resolved | Resolved | Release 1A
42 | Quotation Status not displaying on Quote Summary page | 2025-09-18 | Client | Functional | Kishore |  | 2025-09-19 | Resolved | Resolved | Release 1A
43 | Change subcategory product to Products and use same product page as quotation management | 2025-09-18 | Client | Functional | Shekar |  | 2025-09-19 | Resolved | Resolved | Release 1A
44 | qty selector does not let you edit properly on cart page | 2025-09-18 | Client | Functional | Sumukesh |  | 2025-09-19 | Resolved | Resolved | Release 1A
45 | Save as draft not actually saving as draft it appears to be the same as the generate quote page, no way to edit | 2025-09-18 | Client | Functional | Kishore |  |  | Resolved | Resolved | Release 1A
46 | Even though we have less records in page, getting scroll bar in content area |  |  |  | Shekar |  | 2025-09-19 | Resolved | Resolved | Release 1A
47 | LME Price display based on Role Sales Reps & US APAR Sales Executives → Display LME in $ per lb Admin / Super Admin Users → Display LME in $ per MT (if technically feasible based on user login credentials) |  |  |  | Praneeth |  |  | Resolved | Resolved | Release 1A
48 | Customers list has to comes as Role based Ex: If MR is loggedIn, MR's customers list has to populate Apar sales executive loggedIn, All MR's assigned to his account suppose to see there Customers. Super admin and Admin to see all customers |  |  |  | RK/Kishore |  | 2025-09-19 | Resolved | Resolved | Release 1A
49 | Quotations list has to come as Role based. Ex: If MR is loggedIn, MR's customers list has to populate Apar sales executive loggedIn, All MR's assigned to his account suppose to see there Quotations. Super admin/ Admin to see all quotations |  |  |  | RK/Kishore |  |  | Resolved | Resolved | Release 1A
50 | Can you please set the warning of less than MOQ to pop up only when user clicks on recalculate? At Product selection & Cart&Commerical Page |  |  |  | Sumukesh |  | 2025-09-23 | Resolved | Resolved | Release 1A
51 | Impement Bulk Data import for all Masters - Admin access |  |  |  | Sumukesh | 2025-10-30 |  | Open | Open | Release 1B
52 | SKU Selection & Product Search: Non-standed (e.g., MV cables, UL codes) |  |  |  | Sumukesh/Kishore |  |  | Open | Open | Phase-II
53 | Non-Standard RFQ’s: Manual entry form for non-standard RFQs with Notes/comments field in quotes for custom requests |  |  |  | Sumukesh/Kishore |  |  | Open | Open | Phase-II
54 | Quote Generation: Ability to download Quotation in PDF in agent-presentable format |  |  |  | Sumukesh |  |  | Resolved | Resolved | Release 1A
55 | Quote Type Identification: Track metrics for bid and buy separately |  |  |  | Kishore |  |  | Resolved | Resolved | Release 1A
56 | Refresh Quote: Ability to refresh quotes |  |  |  | RK/Kishore | 2025-10-08 | 2025-10-08 | Resolved | Resolved | Release 1B
57 | Pricing Engine: Specila approal workflow development - VA% back calculation - Ability to adjust pricing based on Reel length logic - Port/container configuration - Container loadability: Ability to do Container adjustment if product value < container capacity |  |  |  | Sumukesh/Kishore |  |  | Open | Open | Release 1B
58 | Search products by Favourites List (Add to Favourites) |  |  |  | Sumukesh/Kishore |  |  | Hold | Open | Phase-II |  |  | Moved to Phase II as per discurss on 10th Oct
59 | Search products by Past orders or frequently ordered items |  |  |  | Sumukesh/Kishore |  |  | Hold | Open | Phase-II |  |  | Moved to Phase II as per discurss on 10th Oct
60 | Quote Versioning & Tracking: Track quote-to-order flow (even if PO is offline) Tracking of defined KPIs |  |  |  | RK/Praneeth |  |  | Hold | Open | Release 1B
61 | Internal sales KPIs - quote-to-order, quote rejection reasons Dashboard for Admin: Create KPI cards (Quotes Created, Success full Quotes, Revenue and etc ) Daily Quote Metrics (KRA) Number of Confirmed Quotes Month-wise Quotation Trend (Chart/Graph View) Day-to-Day Activity Report Customer - Quote Status Summary in Graph view Total Quote Value and Conversion Summary |  |  |  | RK/Praneeth | 2025-10-10 |  | Resolved | Resolved | Release 1B |  |  | Create a procedure for the admin and super admin
62 | manufacturing rep should be auto selected and disabled for editing for quotation and customer creation when the user type is manufacturing rep or mini user |  |  |  | Sumukesh |  | 2025-09-22 | Resolved | Resolved | Release 1A |  |  | Disible the dropdown (Manufacturing rep, customer) when we are going for edit in enqury form
63 | User Management - Edit User - First name, Last name, Mobile no to change |  |  |  | Praneeth |  |  | Resolved | Resolved | Release 1A
64 | Sector C&L change due to long text |  |  |  | Kishore |  | 2025-09-19 | Resolved | Resolved | Release 1A
65 | Currently getting this error when trying to generate quote from manufacturing rep: Failed to generate PDF Refered to the screenshot in teams group |  |  |  | RK |  |  | Resolved | Resolved | Release 1A |  |  | Need to verify and confirm
66 | the address thing needs to be changed For adding an address in customer use this as a reference: https://www.allbirds.com/cart/41301563080784:1 |  |  |  | RK/Kishore | 2025-10-10 |  | Resolved | Resolved | Release 1B
67 | Verification code email is still coming even though not required for new users |  |  |  | Praneeth |  | 2025-09-22 | Resolved | Resolved | Release 1A
68 | Date range filters implementation in the Dashboard |  |  |  | Shekar/Praneeth |  | 2025-10-08 | Resolved | Resolved | Release 1A
69 | Integration with S3 bucket - Quotation PDF |  |  |  | Sumukesh | 2025-10-13 | 2025-10-14 | Resolved | Resolved | Release 1B |  |  | Testing pending
70 | Quotation - Email Notifications |  |  |  | RK | 2025-10-13 |  | Resolved | Resolved | Release 1B |  |  | Email alerts (Quote generated, Quote expired, Approval required, etc.)
71 | Constants |  |  |  | RK/Praneeth | 2025-10-10 |  | Resolved | Open | Release 1B |  |  | Testing pending
72 | Configurations |  |  |  | RK/Praneeth | 2025-10-10 |  | Hold | Open | Release 1B |  |  | Pages need to update
73 | Audit-log |  |  |  | RK/Praneeth | 2025-10-13 |  | Hold | Open | Release 1B
74 | When re-calculate, Color is getting null |  |  |  | RK |  | 2025-09-22 | Resolved | Resolved | Release 1A
75 | Product List having UI Issues.. Image is to big, Remove color and Reel length options. Make userfriendly design. |  |  |  | Shekar |  |  | Resolved | Resolved | Release 1A | Kishore |  | Need to check with Aditya on the color and real length
76 | Constants implimentation in application |  |  |  | Praneeth | 2025-10-10 | 2025-10-07 | Resolved | Open | Release 1B |  |  | Pages need to update
77 | Apar new logo has to reflect in Application and in PDF's |  |  |  | Shekar |  |  | Resolved | Resolved | Release 1A | Kishore
78 | Product Selection page latency and all category is getting an error. |  |  |  | Sumukesh |  | 2025-09-30 | Resolved | Resolved | Release 1A | Kishore
79 | Report submenus are not displaying in QA. Even though Role permissions are added |  |  |  | Sumukesh |  |  | Resolved | Resolved | Release 1A | Kishore
80 | For Admin, Role permissiosn save changes are not wokring.. Getting an error messages |  |  |  | RK |  |  | Resolved | Resolved | Release 1A | Kishore
81 | For Products page, When I toogle handburger menu, Products page is not responsive |  |  |  | Shekar |  |  | Resolved | Resolved | Release 1A | Kishore
82 | Dummy image is getting loaded in cart items.. When we clikc on edit quotation and click on cart items |  |  |  | RK |  | 2025-10-06 | Resolved | Resolved | Release 1A | Kishore
83 | For Manufacturing Reps and APAR Sales Executive display the LME in $ per lb throughout the portal and Quote pdf as well. Example: Last day’s Closing LME Prices (SEP 23RD 2025) AL: 1.3447 $/lb CU: 4.9520 $/lb For Admin/Super Admin display the LME in $ per MT.The LME displayed should be as per Last day closing time. |  |  |  | Shekar |  |  | Resolved | Resolved | Release 1A |  | 2025-09-26 | Only content change
84 | We are still getting Verification code in email kindly remove this since we are not using the verification code anymore. |  |  |  | Shekar |  |  | Resolved | Resolved | Release 1A |  | 2025-09-26 | Its already fixed
85 | Kindly change the hr@bigtapp analytics <noreply> email which will be provided by the team |  |  |  | Malli |  |  | Resolved | Resolved | Release 1A |  | 2025-09-26 | Waiting for Apar team for email
86 | Once the user logs in please make the user remain logged in for his ease of use such that the use need not log in every time, unless the user selects log out from his login. |  |  |  | Sumukesh |  |  | Resolved | Resolved | Release 1A |  | 2025-09-26 | As a standard practice, we use session/token timeout after some time. Currently I think it is around 4 hours.
87 | The logged in manufacturing reps should not see the quotations and customers of other manufacturing reps.Mini users should not see the quotations and customers of other manufacturing rep mini users. |  |  |  | Shekar |  |  | Resolved | Resolved | Release 1A |  | 2025-09-26 | It already fixed
88 | Please provide LME for admin ($ per MT) in 2 decimal ex: AL:$1.3477 CU:$4.9520 |  |  |  | Shekar |  |  | Resolved | Resolved | Release 1A |  | 2025-09-26 | We followed reference south wired 4 decimal places. Will fix it.
89 | Please check the LME for manufacturing rep since it is not tallying with the calculations. Kindly compare with Southwire website values. For the given LME 2689.5 $/MT when we convert this value to $/lb by dividing it by 2204.62 ( 1 MT = 2204.62) it comes around 1.22 but 1.34 was displayed on the portal. |  |  |  | Shekar |  |  | Resolved | Resolved | Release 1A |  | 2025-09-26 | Change the calculation. We will fix it
90 | In quote history I found, 90 degree Celsius with special characters as shown below (90A^oc) |  |  |  | Sumukesh |  | 2025-09-30 | Resolved | Resolved | Release 1A |  | 2025-09-26 | Not a code issue, It a data issue.
91 | Manufacturing Rep name error: in manufacturing rep dropdown |  |  |  | Shekar |  |  | Resolved | Resolved | Release 1A |  | 2025-09-26 | It is fixed, need to cross check.
92 | Link for corporate – Apar usa.com when clicked on apar logo, it should not navigate to the dashboard instead it should lead to aparusa.com (please check with Mr. Charuhas) |  |  |  | Shekar |  |  | Resolved | Resolved | Release 1A |  | 2025-09-26 | It will be redirected to poral.aparusa.com (Will discuss)
93 | Based on user role, display most useful KPI in the dashboard (will be explained to you on/before reviewing the dashboard) |  |  |  | RK/Praneeth | 2025-10-10 |  | Resolved | Resolved | Release 1B |  | 2025-09-26 | Same issue as 62
94 | Rep/salesperson list is empty even if it has been added (in some of the forms please check) |  |  |  | Kishore |  |  | Resolved | Open | Release 1A |  | 2025-09-26 | Pending with Client
95 | Show all the “Mini User “ as “Inside Sales”. The Mini User term is changed to Inside Sales. Mini user is just for our understanding, inside sales is the proper naming for the users added by manufacturing reps |  |  |  | Sumukesh |  | 2025-09-30 | Resolved | Resolved | Release 1A |  | 2025-09-26 | Will update.
96 | Manufacturing rep should be able to Add and delete miniusers (please check in all the forms – will be explained to you adding this point as a reminder) |  |  |  | Sumukesh |  |  | Resolved | Resolved | Release 1A |  | 2025-09-26 | It’s already available in user management (we have inactive provision), will discuss
97 | Where ever In the website is “Customer” change it to “Account” |  |  |  | Shekar |  |  | Resolved | Resolved | Release 1A
98 | Date format SEP 23RD 2025 to be maintained across the website and the quote PDF Example: change the quotation date and expiry date format in the above – quotation summary.Where ever In the website is “Customer” change it to “Account” In the New customer addition form: |  |  |  | Shekar/Kishore |  |  | Resolved | Resolved | Release 1A |  | 2025-09-26 | Will fix it.
99 | New customer addition form, the validation is only for the Indian mobile number please allow user to fill USA mobile number |  |  |  | Shekar |  |  | Resolved | Resolved | Release 1A |  | 2025-09-26 | Will fix it
100 | Change Account website to just Website. And the placeholder should have “www.example.com” |  |  |  | Shekar |  |  | Resolved | Resolved | Release 1A |  | 2025-09-26 | Will fix it.
101 | All non editable fields into grey and disabled. Colour change. |  |  |  | Shekar |  |  | Resolved | Resolved | Release 1A |  | 2025-09-26 | Will fix it
102 | Apar sales executive in the new cust. Addition form is empty it should be auto tagged, disabled and displayed in grey |  |  |  | Kishore |  |  | Resolved | Resolved | Release 1A |  | 2025-09-26
103 | In the contacts section of the new customer addition form: Change Role to Department |  |  |  | Kishore |  |  | Resolved | Resolved | Release 1A |  | 2025-09-26 | Will fix
104 | Keep a check box – Billing address same as Shipping address. |  |  |  | Kishore | 2025-10-11 | 2025-10-08 | Resolved | Resolved | Release 1B |  | 2025-09-26 | Not possible, we are fetching the data based on Zip Code.
105 | Please note create quote button from the customer view page is not working |  |  |  | Shekar |  | 2025-10-08 | Hold | Open | Release 1B |  | 2025-09-26 | Will fix / As of now we are commented the create quote button
106 | Please add item number to the cart page and cart page history |  |  |  | Kishore |  |  | Resolved | Resolved | Release 1B |  | 2025-09-26 | Will disable it for now, and provide this feature in release 2.
107 | New Quote creation form: The order of the fields shown on the quote creation form should be rearranged as per below: Remove: Quote Number * Quote Date * Quote Status * Rearrange as below: Manufacturing Rep * Apar Sales Executive * Customer * Contractor Name * End Customer Job Name * Sector * Destination Port * Bill To Address * Ship To Address * Enquiry Type * Price Basis * Quote Expiry * |  |  |  | Kishore |  |  | Resolved | Resolved | Release 1A |  | 2025-09-26 | Currently it is as per the wireframe. Will do it in release 2.
108 | When trying to fill Bill to and Ship to address directly without entering Customer name, then it should throw a warning message, “Please fill the Customer name” |  |  |  | Kishore |  |  | Resolved | Resolved | Release 1B |  | 2025-09-26 | Currently it is as per the wireframe. Will do it in release 2.
109 | When trying to fill Apar sales executive name directly without entering manufacturing rep name, then it should throw a warning message, “Please fill the Manufacturing rep name” |  |  |  | Kishore |  |  | Resolved | Resolved | Release 1A |  | 2025-09-26 | Will Fix
110 | When trying to fill contractor name directly without entering Customer name, then it should throw a warning message, “Please fill the Customer name”. And so on wherever dependency exists. |  |  |  | Kishore |  |  | Resolved | Resolved | Release 1A |  | 2025-09-26 | Fixed
111 | Please reduce the image size and make it legible |  |  |  | Shekar |  |  | Resolved | Resolved | Release 1A |  | 2025-09-26 | Will Fix
112 | Change the All Categories to All Products |  |  |  | Sumukesh |  | 2025-09-30 | Resolved | Resolved | Release 1A |  | 2025-09-26 | Will Fix
113 | Once All products are selected it should be shown on the drop down “All Products” |  |  |  | Sumukesh |  | 2025-09-30 | Resolved | Resolved | Release 1A |  | 2025-09-26 | Will Fix
114 | please change to 127 mm2 |  |  |  | Sumukesh |  | 2025-09-30 | Resolved | Resolved | Release 1A |  | 2025-09-26 | Data Issue.
115 | In the Cart page when we consider the case where the user alters the quantity but forgets to re-calculate. Then the price should change dynamically without selecting recalculate again or it should prompt the user with warning message – “Please recalculate to proceed with the updated quantity” |  |  |  | Sumukesh |  | 2025-09-30 | Resolved | Resolved | Release 1A |  | 2025-09-26 | Need to discuss - Kishore
116 | When the product category is selected then the filters should change according to data available for the product category. Example: Xhhw has both 1kv and 600 v in voltage grade, if xhhw is chosen from the product category dropdown then the filters 5kv, 10kv, 35kv all should disappear and should only show 1kv and 600 v with number of products in brackets Like Voltage Grade 1kv (30) ☐ 600 v (20) ☐The filters does not need to disappear based on any other filters except product category only. In the above case, even if the user check boxes 1kv (30) , the 600 v (20) option should not disappear. |  |  |  | Sumukesh/RK |  |  | Resolved | Resolved | Release 1A | 2025-10-06 | 2025-09-26 | Will fixed in release 2
117 | In the Quote history, creation time is wrong, please correct |  |  |  | Kishore |  |  | Resolved | Resolved | Release 1A |  | 2025-09-26 | Will fix
118 | In the Quotation summary also change the pid with color |  |  |  | Kishore |  |  | Resolved | Resolved | Release 1A |  | 2025-09-26 | Will fix.
119 | Product selection page loading – slow |  |  |  | Sumukesh |  | 2025-09-30 | Resolved | Resolved | Release 1A |  | 2025-09-26 | Will fix.
120 | Please do not allow user to create cart page with 0/no products |  |  |  | Sumukesh |  | 2025-09-30 | Resolved | Resolved | Release 1A |  | 2025-09-26 | Will fix
121 | Please add the latest product master with updated description since I am unable to find FT rated products in the search, |  |  |  | Sumukesh |  |  | Resolved | Resolved | Release 1A |  | 2025-09-26 | Will fix.
122 | Quotation PDF changes: |  |  |  | Sumukesh/Shekar |  |  | Resolved | Resolved | Release 1A |  | 2025-09-26 | UI is completed and impliment is pending
123 | For FOB, when I generate Quote, the quote is still getting saved as DDP. Even from the Quotation history I can find only the DDP generated quote. Check this quote : APAR/SA/0925/00081-v1 where I selected Generate Quote for FOB India Stock but I got DDP in cart page. in the Quote PDF as well. |  |  |  | Sumukesh |  | 2025-09-30 | Resolved | Resolved | Release 1A |  | 2025-09-29
124 | Transfer of existing Manufacturing Rep customers, quotations and his mini users to another Manufacturing Rep |  |  |  | Kishore |  |  | Open | Open | Phase-II
125 | All products Error - (drop down) error. |  |  |  | Shekar |  | 2025-10-08 | Resolved | Resolved | Release 1A |  | 2025-10-06
126 | MOQ error message in Cart page – please display at the cell level like product selection page not commonly at the top – Red near recalculate button |  |  |  | Kishore |  |  | Resolved | Resolved | Release 1A |  | 2025-10-06
127 | When user changes the qty in the cart page and forgets to recalculate, then the Generate quote is disabled. Only after the user recalculates for any change In the value then generate quote is enabled – near generate button quote warning: Please recalculate for edited qty entered |  |  |  | Kishore |  |  | Resolved | Resolved | Release 1A |  | 2025-10-06
128 | Please consider the latest product master sent to you on 30-10-2025 since it has corrected numbers - Aditional coloum is added for products order in the sheet |  |  |  | Sumukesh | 2025-10-31 |  | Open | Open | Release 1B |  | 2025-10-06
129 | When the user enters the value then the portal should dynamically recalculate the Price without selecting the recalculate button – please provide feasibility and timeline |  |  |  | Kishore |  |  | Open | Open | Phase-II |  | 2025-10-06 | Need to discurss
130 | Tech sheet download in the product list view page, please add the download icon in the products view page |  |  |  | Shekar |  | 2025-10-08 | Resolved | Resolved | Release 1A |  | 2025-10-06 | for all products not loadng
131 | Please provide edit quote button in the quotation summary page |  |  |  | Kishore |  |  | Resolved | Resolved | Release 1A |  | 2025-10-06
132 | Destination port and FOB/DDP , India/USA stock – in the Quotation summary page and in the Quotation PDF, if already added then please ignore |  |  |  | Sumukesh/Kishore |  |  | Resolved | Resolved | Release 1A |  | 2025-10-06
133 | Product list view page – color and reel length dropdown please change the “Select Color” or “Select Reel length” to “Options available” |  |  |  | Shekar |  | 2025-10-08 | Resolved | Resolved | Release 1A |  | 2025-10-06 | Need to discurss
134 | Remove the one of the color dropdowns, it is redundant here. |  |  |  | Shekar |  | 2025-10-08 | Resolved | Resolved | Release 1A |  | 2025-10-06 | Need to discurss
135 | Icon of products – Please make the icons something related to Cables |  |  |  | Shekar |  | 2025-10-08 | Resolved | Resolved | Release 1A |  | 2025-10-06
136 | In the product selection page, when for same product the more qty is added then Cart icon changes to “Update icon” and resets to Cart icon when any change In the color, qty and reel length. Finally, only when user click on the cart icon then the product is added to the cart. |  |  |  | Kishore |  |  | Not an issue | Open | Release 1A |  | 2025-10-06 | Not an issues
137 | Adding new qty for existing product in the cart à warning message “Would you like to add this Qty to the existing cart ? “ |  |  |  | Kishore |  |  | Resolved | Resolved | Release 1A |  | 2025-10-06
138 | Any Total of unit price remove from cart/commercial page and Quotation PDF |  |  |  | Shekar |  | 2025-10-08 | Resolved | Resolved | Release 1A |  | 2025-10-06 | Need to discurss
139 | Manufacturing Rep – preselected and disabled in new quotation creation form instead of dropdown currently showing from manufacturing rep login |  |  |  | Kishore |  |  | Resolved | Resolved | Release 1A |  | 2025-10-06
140 | Default Active filter is not working in the User listing page, as you can see the active filter is ON, still the inactive users are also displayed |  |  |  | Shekar |  | 2025-10-08 | Resolved | Resolved | Release 1A |  | 2025-10-06
141 | Please add FOB/DDP and India/US stock in quotation summary page as well |  |  |  | Kishore |  |  | Resolved | Resolved | Release 1A |  | 2025-10-08
142 | wherever there is "Unit price" please add - ($/1000 FT) wherever there is "Total price" please add - ($) |  |  |  | Shekar |  | 2025-10-08 | Resolved | Resolved | Release 1A |  | 2025-10-08
143 | Product List view and Grid view |  |  |  | Kishore |  |  | Open | Open | Phase-II |  |  | Moved to Phase II as per discurss on 10th Oct
144 | Add Favourites icon need to add in the product selection page and convert as a Favourites the product |  |  |  | RK/Kishore | 2025-10-13 |  | Open | Open | Phase-II |  |  | favourites product will be based on the product Code only not releate any filter selection
145 | In Products page, Lazy loading is not working/implemented. Make sure it is working fine as same as like production selection screen. And also it should work without login |  |  |  | Sumukesh | 2025-10-31 |  | Open | Re-open | Release 1B | Without login is Not Working |  | Should be released in this build
146 | Please implement header collapse when scroll to bottom |  |  |  | Shekar | 2025-10-09 |  | Resolved | Resolved | Release 1B
147 | Master screen: Searching Productname in search bar not working |  |  |  | Praneeth | 2025-10-11 | 2025-10-19 | Resolved | Resolved | Release 1B
148 | creating the account with Manfacturing rep. but getting the manufacturing rep is manually in the dropdown but want it dynamic. |  |  |  | Kishore | 2025-10-11 |  | Resolved | Resolved | Release 1B
149 | quotation management model quotations status filter is not working for expiry status. |  |  |  | Kishore | 2025-10-11 |  | Resolved | Resolved | Release 1B
150 | In Indivudual account, freequently orderd products should be displayed (3rd tab) with 3 months logic - UI Integration |  |  |  | Praneeth/RK | 2025-10-31 |  | Open | Open | Release 1B
151 | Role permission Master: Rename Customer to Accounts in permission Matrix |  |  |  | Shekar | 2025-10-11 |  | Resolved | Resolved | Release 1B
152 | Give permission to view the products but getting the permission to delete, edit and add. |  |  |  | Sumukesh | 2025-10-31 |  | Open | Re-open | Release 1B
153 | Account Screens - product history and quote history Search is missing |  |  |  | Shekar | 2025-10-13 |  | Resolved | Resolved | Release 1B
154 | When iam trying to create New Account redirecting to Dashboard / If there is no permission for the add , Disable the addAccount Button. Check for all Roles specially Apar Sales |  |  |  | Praneeth | 2025-10-13 |  | Resolved | Resolved | Release 1B
155 | LME Price master Edit functionality missing |  |  |  | RK/Shekar | 2025-10-31 |  | Open | Open | Release 1B
156 | LME scheduler and tracking not working (Inactive, active, validtion jobname,duplicate |  |  |  | RK/Shekar | 2025-10-31 |  | Open | Open | Release 1B
157 | Login session to be maintain forever |  |  |  | Sumukesh | 2025-10-11 |  | Resolved | Open | Release 1B
158 | 1. Draft unable to edit – only if we refresh & getting error “failed to update” |  |  |  | Kishore | 2025-10-14 |  | Resolved | Resolved | Release 1A
159 | 2. All products not visible in the dropdown product selection |  |  |  | Shekar | 2025-10-14 |  | Resolved | Resolved | Release 1A
160 | 3. Lazy loading – not working if we refresh only (same as 145) |  |  |  | Sumukesh | 2025-10-31 |  | Open | Re-open | Release 1A
161 | 4. Only if we refresh, some capabilities are working |  |  |  | Kishore | 2025-10-14 |  | Resolved | Resolved | Release 1A
162 | 5. Even if the Product is deleted, it shows pop up message that a product exists and the |  |  |  | Kishore | 2025-10-14 |  | Resolved | Resolved | Release 1A
163 | 6. IF refresh from the product selection it should stay in cart page/ but goes back to enquiry form page |  |  |  | Kishore |  |  | Open | Open | Phase-II
164 | 7. If the user changes the qty, where he does not select recalculate after that he changes it to same qty and selects recalculate it shows different value. |  |  |  | Kishore | 2025-10-14 |  | Resolved | Resolved | Release 1A
165 | 8. India/US stock not present |  |  |  | Sumukesh | 2025-10-14 |  | Resolved | Resolved | Release 1A
166 | 9. Unique id like pid add to quotation pdf |  |  |  | Sumukesh | 2025-10-14 | 2025-10-14 | Resolved | Resolved | Release 1A
167 | 10. Both pre tariff columns required in the cart page and quotation pdf |  |  |  | Sumukesh | 2025-10-14 |  | Resolved | Resolved | Release 1A
168 | 11. Quote No: India FOB delivery -2-3 weeks and USA delivery in weeks – which is opposite to the logic, India FOB - APAR/CB/1025/00029-V1 |  |  |  | RK | 2025-10-14 |  | Resolved | Resolved | Release 1A
169 | 12. All reel length options should be displayed in the single product view page |  |  |  | Kishore | 2025-10-14 |  | Resolved | Resolved | Release 1A
170 | 13. Alternate colors in the quotation pdf table |  |  |  | Sumukesh | 2025-10-14 | 2025-10-14 | Resolved | Resolved | Release 1A
171 | 14. Centre align the values in the quotation – except Description |  |  |  | Sumukesh | 2025-10-14 | 2025-10-14 | Resolved | Resolved | Release 1A
172 | 15. Update the Product master with new coloum ORDER BY, based on the new excel sheet show the order on the quotation table (same as 128) |  |  |  | Sumukesh |  |  | Open | Open | Phase-II
173 | 16. Remove “Remarks” from pdf |  |  |  | Sumukesh | 2025-10-14 | 2025-10-14 | Resolved | Resolved | Release 1A
174 | 17. Title make it Bold (first line of description) in quotation pdf |  |  |  | Sumukesh | 2025-10-14 | 2025-10-14 | Resolved | Resolved | Release 1A
175 | 18. All products in the product selection or All status in user mgmt. page – it is empty |  |  |  | Shekar | 2025-10-14 |  | Resolved | Resolved | Release 1A
176 | 19. Remove increase/decrease arrow buttons from the qty in the cart & commercial page |  |  |  | Shekar | 2025-10-14 |  | Resolved | Resolved | Release 1A |  | 2025-10-16
177 | Pagination Issue > When u are in 41-50 page Select any filter Quotations are apraing in last Page , It must have to start Between the 1-10 |  |  |  | Kishore |  |  | Resolved | Resolved | Release 1B |  | 2025-10-16
178 | Images getting Small sizes in Products Pages categories :MV EPR,MV TR-XLPE,RHH/RHW-2,UD,UDR |  |  |  | Shekar |  |  | Open | Re-open | Release 1B |  | 2025-10-16 | images getting small again previous build working fine
179 | Manufature rep >>Edit >> Current Manufacturing Rep is not available now. Please change the manufacturing representative.>> Pop-up message appearing for users while editing |  |  |  | Praneeth |  | 2025-10-19 | Resolved | Resolved | Release 1B |  | 2025-10-16
180 | Manufature rep >> Only Manufature rep lniked users Must appeard in the userlist ,Not all Miniusers |  |  |  | Praneeth |  | 2025-10-19 | Resolved | Resolved | Release 1B |  | 2025-10-16
181 | Inside Sales >> Inside sales are not dispalying They must have to Display linked Manufature reps |  |  |  | RK/Praneeth | 2025-10-31 |  | Open | Re-open | Release 1B |  | 2025-10-16
182 | Display Only MF and IS linked to their Particular AparSales Executive |  |  |  | RK/Praneeth | 2025-10-31 |  | Open | Re-open | Release 1B |  | 2025-10-16
183 | Restrict the roles Dropdown as per the user ASE can ahve to see the dropdown only MF,Inside sales Only .It is Displayng Admin,AparSalesexecutive also |  |  |  | RK/Praneeth | 2025-10-31 |  | Open | Open | Release 1B |  | 2025-10-16 | Login with ASe role filter is showing ASE Restrict ASe
184 | 1. Manufacturing Rep name is not displayed in the edit user from Manufacturing Rep login - Resolved |  |  |  | Praneeth |  |  | Resolved | Resolved | Release 1A |  | 2025-10-16
185 | 2. To a Manufacturing Rep, the inside sales of Other Manufacturing is displayed - Resolved |  |  |  | Praneeth |  |  | Resolved | Resolved | Release 1A |  | 2025-10-16
186 | 3. Create Quotation form - change all the "Customer" to "Account" - Pending |  |  |  | Kishore |  |  | Resolved | Resolved | Release 1A |  | 2025-10-16
187 | 4. Account Category to be hidden for Manufacturing rep and Inside sales rep - Working fine |  |  |  | Kishore |  |  | Resolved | Resolved | Release 1A |  | 2025-10-16
188 | 5. Address - new format - Release 1B |  |  |  | Kishore |  |  | Resolved | Resolved | Release 1B |  | 2025-10-16 | Pending form client confirmation
189 | 6. "All Products" in the dropdown is not displayed on the dropdown in the single product view page - Resolved |  |  |  | Shekar |  |  | Resolved | Resolved | Release 1A |  | 2025-10-16
190 | 7. Please check - when Manufacturing rep tries to open single product view page - it shows an error "Insufficient permission to access" - for Manufacturing Rep login - Resolved |  |  |  | Shekar |  |  | Resolved | Resolved | Release 1A |  | 2025-10-16
191 | 8. download tech sheet button to be added near the CART icon - Resolved |  |  |  | Kishore |  |  | Resolved | Resolved | Release 1A |  | 2025-10-16
192 | 9. Quantity Bug - check - Resolved |  |  |  | Kishore |  |  | Resolved | Resolved | Release 1A |  | 2025-10-16
193 | 10. "Are you sure you want to exit? " Confirmation box before the user exits the cart & commercial page - Phase-II |  |  |  | Kishore |  |  | Open | Open | Phase-II |  | 2025-10-16
194 | 11. Any refresh it goes back to the enquiry form - this should stay on the page after refresh - Phase-II |  |  |  | Kishore |  |  | Open | Open | Phase-II |  | 2025-10-16
195 | 12. When hovered over eye icon - " View product"- Resolved |  |  |  | Kishore |  |  | Resolved | Resolved | Phase-II |  | 2025-10-16
196 | 13. When hovered over download icon - " Download Technical Datasheet" - Resolved |  |  |  | Kishore |  |  | Resolved | Resolved | Release 1A |  | 2025-10-16
197 | 14. Insulation level in the single product view page, remove the circle if the insulation level is not applicable for the product- Resolved |  |  |  | Kishore |  |  | Resolved | Resolved | Release 1A |  | 2025-10-16
198 | 15. Product order to display in the product selection page will be shared with you later |  |  |  | RK |  |  | Resolved | Resolved | Release 1B |  | 2025-10-16
199 | in Products list filter is not working properly |  |  |  | Shekar |  |  | Resolved | Resolved | Release 1B |  | 2025-10-16
200 | LME Schedular and Tracking |  |  |  | RK/Praneeth | 2025-10-31 |  | Open | Open | Release 1B
201 | Adding Multiple Address Not showing in the page |  |  |  | Sumukesh/Kishore |  |  | Resolved | Resolved | Release 1B
202 | Product Selection Page: 1. Product Category filter not working 2. Tech sheet download not working in product selection page 3. Product Order not working |  |  |  | Sumukesh | 2025-10-29 | 2025-10-29 | Resolved | Resolved
203 | New Account Addition form – Mobile number Validation – for US country code displaying warning “Enter a valid 10 Digit Indian mobile number” |  |  |  | Sumukesh | 2025-10-29 | 2025-10-29 | Resolved | Resolved
204 | Tech sheet download not available in the product details page |  |  |  | Sumukesh | 2025-10-29 | 2025-10-29 | Resolved | Resolved
205 | Any Search in the Product Master page, is leading to blank screen in MASTERS – product master |  |  |  | Sumukesh | 2025-10-29 | 2025-10-29 | Resolved | Resolved
206 | Pricing configurations Page: 1. Sea Freight can be removed 2. The Duty & Surcharge should be configurable, and separate for Al and Cu. If the value of AL: 3.2% and Cu: 4% should be changeable by the Admin |  |  |  | RK/Sumukesh | 2025-10-29 | 2025-10-29 | Resolved | Resolved
207 | New Inside Sales Addition form – Phone number warnings repeated |  |  |  | RK/Sumukesh | 2025-10-29 | 2025-10-29 | Resolved | Resolved
208 | Please check - when Manufacturing rep tries to open single product view page - it shows an error "Insufficient permission to access" - for Manufacturing Rep login – NOT Resolved but marked as resolved please check |  |  |  | Sumukesh | 2025-10-29 | 2025-10-29 | Resolved | Resolved
209 | In cart & commercial page, if we just change the DDP to FOB or US Stock to India Stock and don’t change any quantity, still it is showing error as “You have unsaved quantity, recalculate” , please make it like previous version where if the user changes the FOB to DDP or vice versa it dynamically displays the DDP/FOB table without selecting recalculate. For US/India stock the user must recalculate the see the updated price. |  |  |  | Kishore |  |  | Open |  |  | To be discussed
210 | Edit Account information: 1. “Street address 2 (Optional) ” instead of “Street Address (Optional)“ 2. Address Type displayed first, then followed by other address information 3. Country - prefilled “USA” and disabled & non editable 4. Remove Search icon |  |  |  | sumukesh | 2025-10-30 | 2025-10-30 | Resolved | Open
211 | When duplicate the quote --> first quote page should open instead of directly replicating the quote | [6 empty] | Open |  |  | To be discussed
212 | Duplicate quote – To create new version - Contractor disabled along with other discussed parameters | [6 empty] | Open |  |  | To be discussed
213 | 3 dots – duplicate the quote, | [6 empty] | Open |  |  | To be discussed
214 | “Favourites” linked to Logged in User |  |  |  | RK/Sumukesh | 2025-10-29 | 2025-10-29 | Resolved | Open
215 | 14. Refresh quotation button inside the edit quotation page | [6 empty] | Open |  |  | To be discussed
216 | 15. “Draft Quote” expiry date & creation date not required. Expiry only for Approved and after 7 days the same approved will be shown as expired. Pending for approval – no expiry date. Expiry date only counted from Status – “Approval date” |  |  |  | Sumukesh/RK | 2025-10-30 |  | Open | Open | Release 1B
217 | 16. When a quotation is changed from draft to approved then the creation date is date it is changed from draft to approved & expiry date also changes (creation + 7 days) accordingly |  |  |  | Sumukesh/RK | 2025-10-30 |  | Open | Open | Release 1B
218 | 17. Link for earlier versions within the quotation summary of latest quotation, show V1, V2, V3 the versions as tabs. When clicked it navigates to the version | [6 empty] | Open |  |  | To be discussed
219 | 18. Quotation history - 3 dots in action – duplicate, create a new version | [6 empty] | Open |  |  | To be discussed
220 | 19. Creation date, approval date and expiry date as separate columns |  |  |  | Sumukesh/RK | 2025-10-30 |  | Open | Open | Release 1B
221 | Everyday LME AL & CU to be displayed in $/1000 MT for all the users |  |  |  | Sumukesh | 2025-10-29 | 2025-10-29 | Resolved | Open
222 | Any status change in Quotation send an email to the Admin and the user who generated the quotation |  |  |  | Sumukesh/RK | 2025-10-30 |  | Open | Open | Release 1B
223 | SPA: 1. Target price: unit price post tariff ($/1000 FT) for each item level 2. Target price post tariff to be placed in between unit price post tariff & total price post 3. Target total price post tariff – where based on the target unit price the total target price post tariff will change when recalculated. 4. By default – unit price post tariff as target price 5. “Submit for Approval” button 6. Admin login: Additional column near Original VA% as Revised VA% 7. The existing columns such as unit price pre tariff, unit price post tariff, total price pre tariff and total price post tariff will change for revised VA%. 8. Reel length non editable but quantity editable in SPA admin cart page |  |  |  | Sumukesh | 2025-10-30 |  | Open | Open | Release 1B
224 | Keep the US country code (+1) as default instead of Indian Country code |  |  |  | Sumukesh | 2025-10-31 |  | Open | Open | Release 1B
225 | Same as Billing/Shipping address is not working |  |  |  | Kishore | 2025-10-31 |  | Open | Open | Release 1B
226 | When adding an address for second time, on the account addition form The non editable Country field throws an error “ Country required” |  |  |  | Kishore | 2025-10-31 |  | Open | Open | Release 1B
227 | While creating a Quotation, Move the option to Select US Stock or India Stock to the first page/Enquiry form The MOQ for US Stock and India Stock are different. So as per the selection the MOQ for each product will change in the product selection page | [6 empty] | Open | Open | Phase-II

## Page level status
Sno | Module | Page Name | Status | Remarks | Owner
1 | Authentication | Login | Completed | Login Page (with Email Verification)
2 |  | Forgot password | Completed | Forgot Password / Reset Password
3 | User Management | User List | Completed
4 |  | User Registration | Completed | Remove 2step authentication
5 |  | User Activation | Completed | Active/Inactive Status
6 |  | Roles | Completed | Create / Edit Roles (Admin, Super Admin, Manufacturing Rep, Apar Sales Executive, Mini User
7 |  | Add Role | Completed
8 |  | Role Permission | Completed
9 | Master Data | Payment Terms | Completed
10 |  | Port | Completed
11 |  | LME Prices | Completed | History of the schedular Page integration is penidng | Shekar
12 |  | Terms and Conditions | Completed | Terms and conditons page is there but need to integreate in pdf view is pening | Sumukesh
13 |  | Delivery Master | Completed
14 |  | VA Percentage | Completed
15 |  | Manufacturing Rep Commissions | Completed
16 | Product Masters | Products | Completed
17 |  | Product Details | Completed
18 |  | Product Category | Completed
19 |  | Conductor Type | Completed
20 |  | Voltage Grade | Completed
21 |  | Insulation | Completed
22 |  | Insulation Level | Completed
23 |  | Outer Jacket | Completed
24 |  | UL Certification | Completed
25 |  | Flame Test | Completed
26 | Customers | Customers List | Completed
27 |  | Create New Customer | Completed
28 |  | Customer Details View | Completed
|  | Product View | Open
29 | Quote Management | Quotation List | Completed
30 |  | Enquiry Form | Completed
31 |  | Product Selection | Completed
32 |  | Cart Page and Commercial Page | Completed
33 |  | Quote Preview | Completed
34 |  | Quotation History | Completed
35 | Notifications | Email Notifications | InProgress | Email alerts (Quote generated, Quote expired, Approval required, etc.) | Sumukesh
36 | Settings | Constants | InProgress |  | RK/Kishore
37 |  | Configurations | InProgress |  | RK/Kishore
39 |  | Audit-log | InProgress |  | RK/Kishore
41 | Reporting & Dashboard | Dashboard | Completed | Need to check
42 |  | Sales Rep Summary | Completed
43 |  | Quotation Status Reports | Completed
44 |  | Sales Commission Reports | Completed
45 |  | Product Summary Reports | Completed
46 |  | Customer Summary Reports | Completed
47 |  | Role Hierarchy | InProgress |  | Praneeth